## Waiver Tracker
Lien Waiver Tracker — by LienDone · liendone.com
Project | Sub / supplier | Tier | Pay app # | Through date | Amount | Retainage withheld | Conditional sent | Payment cleared | Unconditional sent | Phase | Status | Notes
Maple St Office | Apex Concrete | Sub | 3 | 2026-05-31 | 42000 | 4200 | 2026-06-02 | 2026-06-09 | 2026-06-10 | Progress |  | Closed clean
Maple St Office | Ready-Mix Supply Co | Sub-tier | 3 | 2026-05-31 | 11500 | 0 | 2026-06-02 | 2026-06-09 |  | Progress |  | Supplier of Apex — collect too
Harbor Lofts | Volt Electric | Sub | 5 | 2026-05-31 | 28000 | 2800 | 2026-06-03 |  |  | Progress |  | Waiting on owner draw

## How to use
Lien Waiver Tracker — how to use this sheet
The one rule: no check leaves until the conditional waiver is on file.
And no next pay cycle starts until the prior unconditional is back.
The cycle for every sub, every pay period:
1. Send the CONDITIONAL waiver with the pay app. Log the date in 'Conditional sent'.
2. When the draw clears, log the date in 'Payment cleared'.
3. Send the UNCONDITIONAL waiver. Log the date in 'Unconditional sent'.
4. The Status column updates itself. Repeat each period until the job closes.
Status column (filled in for you):
Send conditional — nothing sent yet for this row.
Awaiting payment — conditional sent, draw not cleared.
Need unconditional — draw cleared, unconditional not sent yet. ACT ON THESE.
Closed — unconditional on file. Done.
Don't forget the sub-tiers.
Your sub's waiver only releases THEIR rights. Their unpaid supplier can still lien the job.
Add a row (Tier = 'Sub-tier') for each supplier and lower-tier sub on larger jobs.
Retainage:
Log withheld retention separately. A progress waiver should not release retainage you haven't paid.
When this spreadsheet stops being enough:
Around 5+ active jobs, the parallel states get too many to track by hand and the first waiver slips.
LienDone sends the right form automatically, gates payment on the signature, and tracks every
sub and sub-tier across every job. Stop chasing waivers by email: https://www.liendone.com